## ELMS-Test-Plan.
Sr.no. | Attribute Name | Attribute Description
1 | Test Plan Identifer | Employee Leave Management System
2 | Introduction | Employee Leave Management System is software project developed to maintain the leave records of company's employee and this software is based on the role-based panel for Admin and Employees.It includes departement structure, user management , leave applications and approval flow.
3 | References | SRS Document and ELMS Software https://project2.qualibytes.com/admin/index.php https://project2.qualibytes.com/index.php
4 | Test Items | i] Login Page ii] Admin Page iii] Employee Panel
5 | Features to be Tested | i] Login Page ● Visit the login page. ● Submit credentials (either Admin or Employee). ii] Admin Panel ● Add Departments ● Create Employee Accounts (assign code + password) ● View Leave Requests iii] Employee Panal ● Apply for Leave ● View Status of All Requests
6 | Features to be Not Tested | i] Admim Panel ● Approve/Reject Leave ● View Leave Logs ii] Employee Panal ● See Admin Feedback
7 | Testing Approach | We are performing the Manual Testing and their types i.e. Fuctional Testing , Levels of Testing i.e. Unit Testing , Integration Testing , System Testing and UAT (User Acceptance Testing)
8 | Test Criteria | Entry : All Build Verification tests should passed, Test Environments should set up. Exit : All criteria test cases should executed, open high -severity defects.
9 | Test Deliverables | i] Test Plan ii] Test Cases iii] Test Execution Report iv] Defect Report
10 | Test Environment / Platforms | Operating System : Windows 11 Browser : Brave Database : MySQL
11 | Resource Requirements | Software Testing Tool , Developer, Testers
12 | Test Schedule | Rquirement Analysis : 2 Days Test Plan Document : 2 Days Test Case Document : 1 Days Test Execution : 3 Days Funtional Testing : 3 Days Automation Testing : 1 Week Defect Report : 3 Days
13 | Test Case Management | Testing Approch : Agile Technique Test Case tool: MS Excel Test Case Format: Each test case will incluse: i) Test Case Id ii) Description iii)Preconditions Iv)test steps v)Expected Result vi)Actual Results Vii) Status Viii)Screenshot
14 | Defect Management | Defect Tool: JIRA Defect Process: i)Defects will be categorized by severity (Critical, High, Medium, Low). ii)Each defect will be assigned to the appropriate team member for resolution. iii)After resolution, defects will be retested to confirm fixes. iv)Defects that cannot be fixed during the current testing cycle will be deferred to the next release.
15 | Approval and Signoff | Reviewed by : Test Manager : Sanket P Project Manager : Nilesh W Development Lead: Pranav K Approval Date : 20/10/2026
16 | Roles and Responsibilites | Emp Name | Role | Responsibilty
|  | 1. Raj M | Jr. Tester | Execute the Login Page
|  | 2. Ravindra S | Sr. Tester | Execute the Admin panel
|  | 3.Kalyani M | Sr. Tester | Execute the Employee Panel